## Slide 1: Project: TA Report System
IE04 Weekly Progress Report
2022/10/26
Team: Sauce Katsudon

## Slide 2: Activities of Previous Week
Task | Member | Status | Work Hours
Create class diagram | Tomohito | 100% | 2:00
Create use case diagram + description | Angelita | 95% | 3:00
Create UI wireframe | Angelita | 95% | 4:00
Read Django documentation (getting started) | Angelita | 100% | 1:30
Setting up environment | Angelita | 100% | 3:00
Updated product backlog | Angelita | 100% | 1:00
Added setting up environments information to repository | Angelita | 100% | 1:30
 |  | Total time: | 16:00

## Slide 3: Plan for This Week
Task | Member | Work Hours
Hello world | All | 0:30
Make phase backlog + detailed task description | Angelita | 2:00
Create phase 1 product | All | 10:00
 | Total time: | 22:30

## Slide 4: Phase Task Board
To Do
Phase backlog
Login page UI
Main page UI
Server side code for login request
In Progress
In Review
Use case diagram
Class diagram
UI wireframe
Done
Product backlog
Hello world

## Slide 5: Issues & Risks (*if any)
Problem
Cause
Possible Solution
Deadline