## Slide 1: Project: TA Report System
IE04 Weekly Progress Report
2022/10/19
Team: Sauce Katsudon

## Slide 2: Activities of Previous Week
Task | Member | Status | Work Hours
Create user stories | Tomohito | 100% | 2:00
Create user stories | Angelita | 100% | 2:00
Combine user stories and create product backlog | Angelita | 90% | 4:00
Update README.md | Angelita | 100% | 0:05
 |  | Total time: | 8:05

## Slide 3: Plan for This Week
Task | Member | Work Hours
Make use case diagram | All | 2:00
Make class diagram | All | 2:00
Make phase backlog | Angelita | 2:00
Learn Django | All | 2:00
Hello world | Angelita | 0:30
 | Total time: | 14:30

## Slide 4: Phase Task Board
To Do
Use case diagram
Class diagram
Phase backlog
Hello world
In Progress
Product backlog
In Review
Done

## Slide 5: Issues & Risks (*if any)
Problem
Cause
Possible Solution
Deadline