## Sheet1
Phase 1 Backlog
ID | Task | Member | Priority | Status
1 | Read and understand RFP | All | Must | Done
2 | Research about language and framework | All | Must | Done
3 | Decide language and framework | All | Must | Done
4 | Create user story | All | Must | Done
5 | Create the backlog (whole project) | Angelita | Must | Done
6 | Create user diagram | Angelita | Must | Done
7 | Create class diagram | Tomohito | Must | In review
8 | Create user diagram description | Angelita | Must | Done
9 | Create UI wireframe | Angelita | Must | Done
10 | Learn Django | All | Must | In progress
11 | Set up environment | Angelita / Tomohito | Must | Done / In progress
12 | Add setting up environment information to readme.md | Angelita | Want | Done
13 | Create UI mockups | Angelita | Must | Done
14 | Hello world | Angelita | Must | Done
0