## Sheet1
Phase 2 Backlog
ID | Task | Member | Priority | Status
1 | Learn Django | All | Must | In progress
2 | Create sequence diagram | Tomohito | Must | Done
3 | Setting up environment | Tomohito | Must | Done
4 | Revised class diagram | Angelita | Must | Done
5 | Create project app | Angelita | Must | Done
6 | Design and create models | Angelita | Must | Done
7 | Add models to admin page | Angelita | Must | Done
8 | Improve time display | Angelita | Want | In progress
9 | Create views | All | Must | In progress
0